## Run Plan
2015-10-23 04:30 |  | Goals of 1st commission run
2015-10-23 16:30 |  | Operating TPC with beam
Test Gating Grid
Take data with TPC
setup auxiliary detectors
Analog and discriminator signals for Start, Active collimator, 2 upstream scintillators and veto routed out (16 signals).
TTL_Open and TTLClose disconnected (?) from GG driver.
0.1 mm Sn target
Personnel | I_beam | time | duration | Tasks
Tetsuya/Isobe | 2015-10-23 | 4:30 | 0:30 | check beam rate on Samurai beam plastic before TPC
Tetsuya/Isobe | any | 5:00 | 1:00 | transport beam to TPC and check tuning, turn on voltages of auxiliary devices w/o remote control
Bill/Jon/Justin | any | 6:00 | 1:00 | set voltages and thresholds on scintillator (2-3 iterations)
Bill/Jon/Justin | No beam | 7:00 | 0:30 | estimate misalignment and need to move Katana & TPC
Bill/Jon/Justin | No beam | 7:30 | 0:30 | retune if necessary (change B field, adjust last quad??)
Bill/Jon/Justin | <10 Hz | 8:00 | 1:00 | Slowly raise the voltages on the anodes (<10 Hz)
Bill/Jon/Justin | <10 Hz | 9:00 | 1:00 | data run at mid range of TPC, check beam profile and beam space charge ??
Hyo Sang/Justin/Bill | <10 Hz | 10:00 | 0:30 | Varying the Gating Grid Voltage
Hyo Sang/Justin/Bill | <10 Hz | 10:30 | 0:30 | https://docs.google.com/spreadsheets/d/1UAeDEBw7f1Zr9flBgYRSoDCEhSVmlDeXVp7POSwwoAI/edit#gid=0
Hyo Sang/Justin/Bill | <10 Hz | 11:00 | 0:30
Hyo Sang/Justin/Bill | <10 Hz | 11:30 | 0:30
Hyo Sang/Justin/Bill | <10 Hz | 12:00 | 0:30
Hyo Sang/Justin/Bill | <10 Hz | 12:30 | 0:30 | Raise the anode voltage to the operating voltage. Check again?
Polish group | Max | 13:00 | 1:00 | Check trigger logic
Piotr/Bill | Max | 14:00 | 0:30 | Put trigger into standard mode so that we suppress non-interacted beam.
Jon/Mizuki/Clementine | Max | 14:30 | 0:30 | change to aluminum brick target
Piotr/Bill | Max | 15:00 | 1:30 | Take a long run on the Al “brick” target.
| Max | 16:30 |  | give beam back to IMPACT
Hyo Sang/Justin |  |  | 20 | pulser ramp

## Shifts
SHIFT
Shifts | 22:00 |  |  | 4:00 | Isobe |  |  | Lynch |  | Justin
|  | Manpower |  | 5:00 | Isobe |  |  | Lynch |  | Justin |  | Giordano
|  | beam | Isobe/Mizuki/Suzuki | 6:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Giordano
|  | start/veto scintillator | Clementine | 7:00 | Isobe |  | Clementine | Lynch | Jon | Justin | Yan | Giordano
|  | Katana | Jerzy/Pawel/Piotr/Krzysztof | 8:00 | Isobe | suzuki | Clementine | Lynch | Jon | Justin | Yan | Giordano
|  | Kyoto Array | Tetsuya/Keneko | 9:00 | Isobe | suzuki | Clementine | Lynch | Jon | Hyo Sang | Yan | Genie
|  | Active Veto | Yan Zhang | 10:00 | Isobe |  | Clementine | Lynch | Jon | Hyo Sang | Yan | Genie
|  | TPC | Lynch/Jon/Clementine | 11:00 | Mizuki |  | Clementine | Lynch | Jon | Hyo Sang | Yan | Genie
Shift leader |  | GG | Lee/Justin/Suzuki | 12:00 | Mizuki | suzuki | Clementine | Lynch | Jon | Hyo Sang | Yan | Genie
|  | software | Genie/Giordano | 13:00 | Mizuki | suzuki | Clementine | Lynch | Jon | Hyo Sang | Yan | Genie
|  | Shift Leader | Betty/Mizuki | 14:00 | Mizuki | suzuki | Clementine | Lynch | Jon | Hyo Sang | Yan | Genie
|  |  |  | 15:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang | Yan | Genie
|  |  |  | 16:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang | Yan | Genie
|  |  |  | 17:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang | Yan | Genie
|  |  |  | 18:00 | Mizuki | suzuki | Clementine |  | Jon | Hyo Sang | Yan | Genie
Manpower
[7 empty] | beam | Isobe/Mizuki/Suzuki
[7 empty] | start/veto scintillator | Clementine
[7 empty] | Katana | Jerzy/Pawel/Piotr/Krzysztof
[7 empty] | Kyoto Array | Tetsuya/Keneko
[7 empty] | Active Veto | Yan Zhang
[7 empty] | TPC | Lynch/Jon/Clementine
[7 empty] | GG | Lee/Justin/Lynch
[7 empty] | software | Genie/Giordano
[7 empty] | Shift Leader | Betty/Mizuki
50:00
51:00
52:00
53:00
54:00
55:00
56:00
57:00
58:00
59:00
60:00