## Sheet1
| September |  |  |  | October |  |  |  | November |  |  |  | manpower
| 7-13 | 14-20 | 21-27 | 28-4 | 5-11 | 12-18 | 19-25 | 26-31 | 1-7 | 8-14 | 15-22 | 22-29
Task
Hardware control system
Finish mounting AsAd
Take Cosmic Data
software development
IMPACT
No access starting Oct 21
12 hr. TPC-MS Oct 23?
Commisioning run prep:
Kyoto Multiplicity Trigger Array
Design mount structure
Mount structure check
Trigger out check
Send to RIKEN
Mount on SPiRIT-TPC
Assemble cables
Signal check
KATANA Array
Mount structure check
Discuss about cabling
Trigger out check
Send to RIKEN
Mount on SPiRIT-TPC Rails
Assemble cables
Signal check
Trigger test
cosmic test with TPC and Katana and Kyoto array
target | [12 empty] | 4K, 2P, 1MSU
Target Mechanism
Target Frames
mount target on frames
Install Target
Active Collimator
test AC with flange and cables
instsall AC
test AC trigger
Set up platform | [12 empty] | 4K, 1P, 5MSU,1C
Install TPC on platform
Consider additional tipping due to AsAd cables
Move electronics racks into exerimental area
move gas rack, bottles into exp area
Connect gas to TPC
flush TPC
Connect HV to TPC: cathode, anode wires, GG, target ladder
AsAd to CoBo data connection
AsAd power connection
CoBo rack connected to network
Cooling setup
Ready-to-run checks:
Check trigger
Check data connection out
Take cosmic data & Triggered with Katana, AC, Kyoto array | [12 empty] | 4K, 4P, 6MSU, 1C
Gating Grid
install Kyoto array & test
install Katana array & test
Full testing of TPC, AC, Katana, Kyoto
Ready for beam
Beam
DAQ
on-line analysis
offline analysis